## Work Plan
| 2026 | [5 empty] | 2027
Ad Hoc Mobility Committee Work Tasks | January February | March April | May June | July August | Sept/Oct | Nov/December | January/February | March/April | May/June | July/August | Sept/Oct | Nov/Dec
Update of CTP-HSTP
Discuss Work Program
Public Involvement Plan Draft
Inventory of Existing Services
Public Involvment Plan Implementation
Needs Analysis and Gap Assessment
Update of Demographic Data (Grant)
Get Origin/Destination of Trips (Paratransit) (Survey?)
Develop list of strategies
Group to decide on critiera, points for prioritizing projects
Public Comment Period on Proposed Evaluation Process- TPB Discussion
TPB action on proposed evaluation process
Make required updates to Draft
Present Draft Document to Committee for Review/WSDOT Review before public Comment
Take Draft to TPB for discussion, Public Comment Period
TPB Approval, final Draft Due December 1st to WSDOT
Mobility Management Tasks
Discuss Work Program
Discuss Cadance of In Person Meetings/ Bigger Gatherings
Look at Example Resource Guides to Give Feedback on Format
Focus Group Emergency Management to Scope Work
Continue Stakeholder Interviews with Committee Members (Ongoing)
Use Inventory work done by HSTP to put together resource guide
Have a Draft Resource Guide ready for Committee Approval
Have links to Website for Resource Guide
Brainstorm ways to addresss Gaps uncovered in HSTP Update
Develop possilbe partnerships to address gaps
Possible Large Event to invite stakeholders Cross County
Group Decide to apply for further funding to continue Mobility Management Work
Begin Emergency Management Work
Have Cross County Emergency Management Scenario Planning
Distribute Resource Guide Once Printed
Finalize any interlocal agreements or Partnerships
Write up of Emergency Management Work, take to TPB
Consolidated Grant Tasks
Share Work Plan and discuss role of HSTP update in development of grant criteria
Present Public Outreach (April) and Revised Grant Critieria
Take Proposed Critieria to TPB and Get Public Comment
Finalize criteria for the update with TPB (June)
WSDOT Posts NOFO (June)
Offer times for applicants to get help or work together on applications
Communicate Deadlines and Process for Grant Application
Grant Applications due in GMS
SCOG Application due
Presentations to Committee on Proposed Grants from Committee Members
Committee Ranking of Projects (letter grades)
TPB takes action on the list of projects with Letter Grades
Regional Rankings Due to WSDOT